## 28-11
Date : 29-11-2025
sr# | Delivery Note | Task | Title | Local status (orail25) | Online status (Beta75) | Remark
1 | delivered in R74 | 1787 | chnages in estimate print | done
2 | delivered in R74 | 1828 | Regular tag 15 G | done
3 | delivered in R74 | 1716 | Changes in Bag Print 16 D | done | done
4 | delivered in R74 | 1847 | casting batch bag print | done | done
5 | delivered in R74 | 1844 | Exclusion of customer name & details from PD form print option. | done
6 | delivered in R74 | 1577 | ARTISAN FORM FORMAT | done
7 | delivered in R74 | 1825 | packinglist 7 group s | special case bug given
8 | delivered in R74 | 1854 | need reference no. in jewellery tax invoice | done
9 | delivered in R74 | 1501 | Locker in mrp and bill | done
10 | delivered in R74 | 1867 | changes in packing list 7 & packing list 7 group | done
11 | delivered in R74 | 1914 | new tag | done
12 | delivered in R74 | 1937 | line id wise scan job | done
13 | delivered in R74 | 1939 | Jewelelry Tag 8 B | done
14 | delivered in R74 | 1947 | remove customer code from CS Tag 2 | done
15 | priority : Urgent delivered | 1994 | changes in Quality New tag qr | done
16 | priority : Urgent | 1514 | Tag info New Interface | done
17 | priority : Urgent delivered@24-9-2025 | 1262 | loyal string rfid | done
18 | deliverd in in client without testing @27-8-2025 | 1237 | POS in memo | done
19 | priority : Urgent delivered | S-1 | Application Pull | done | done
20 | priority : Urgent delivered | S-2 | mfg speed up - check on local | done
21 |  | 1874 | job completion date report- future date | done
22 | priority : Urgent delivered | S-3 | mfg speed up - check on local | done
23 | priority : Urgent deliverd: 29-9-2025 | 1935 | bag print O | done | done
24 | delivered without testing | 1946 | speed work- bulk(tagging ) and product alteration archive side up | running
25 | delivered | 1875 | changes in Estimate 1 | done
26 | priority : Urgent delivered | 1962 | changes in Jewellery Tax Summary C | done
27 | priority : Urgent need in client account before diwali | 1966 | customize option in retail bill | done
28 | priority : Urgent delivered | 1970 | worker report pro amendment - add excel export in it. | done | done
29 | delivered | 1976 | Solitaire Purchase and Sale Rate in Material Purchase | done | done
30 | priority : Urgent need in client account after diwali | 1971 | Design Analysis Report - Dynamic Implementation | done done
31 | priority : Urgent need in client account after diwali | 1977 | today metal stock | done | done
32 | priority : Urgent need in client account after diwali | client query - psjewels, elveester | factory outward - query change - due to multiple outward | running
33 | delivered | 1968 | changes in ' sale formate A' excel | done | done
34 | need in R73 priority : Urgent | 1831 | bag print 7B | done | done
35 | priority : Urgent need in client account before diwali | 1967 | received repair rights based | done
36 | priority : Urgent need in client account before diwali | 1965 | Customize Making On Metal Rate | done | done
37 | priority : Urgent delivered | 1942 | Ecommercemodulecoupon code | done
38 | priority : Urgent delivered | 1945 | Ecommerce NewB2Bregistration form | done
39 |  | 1751 | Material Purhcase Return Report - New Design Implementation | bug given | done
40 | need in R74 priority : Urgent | 1509 | Primary Loss Option in Design Master | bug given
41 |  | 1850 | R75 - Regular Flow Bug local | - | bug given
42 |  | 1851 | R75 - Regular Flow Bug Online | bug given
43 |  | 1852 | R75 - Client related Special Case Bug | bug given
44 |  | 1668 | Box and tray sequence in Jewellery Tax Invoice | done
45 |  | 1820 | Box - Tray wise sequence in Sale Format A excel | done
46 |  | 1797 | convert to recat all material sale print | bug given
47 |  | 1842 | WIP Reconcile Status | done | done
48 |  | 1566 | Itask-dynamic Master (smart filter) | done
49 |  | 1597 | need excel and pdf in gst summary report | done
50 |  | 1876 | changes in packing list 7 D group | done
51 |  | 1866 | MISC in Material memo | bug given done | bug given
52 |  | 1769 | Finding in Material Memo | done done | done
53 |  | 1849 | Evo(ref .1170 ) amendment task | -
54 |  | 1570 | Currency amount | done
55 |  | 1899 | Add Dia/CS/MISC/Finding wt column in job transfer history | done | done
56 | priority : Urgent deadline : 26-9-2025 | 1763, | OSR Report | bug given | done
57 |  | 1738 | add search bar while do entry of customer return | done | done
58 |  | 1900 | packing list 7d group in estimate & memo | done
59 |  | 1807 | login details changes | done
60 |  | 1624 | evo(1170)-make cart and wishlist gridview for evo app and website | on hold
61 |  | 1873 | new print ( outsource) | done | done
62 |  | 1872 | Outsource Job Print | done | bug given
63 |  | 1748 | Customer Return Report - New Design Implementation | bug given | done
64 |  | 1752 | Material Sale Report - New Design Implementation | bug given | done
65 |  | 1918 | need gst amount in MRP print 2 GST | done
66 |  | s-4 | speed work- quoation | bug given
67 |  | extra-1 | in support login, wt and pc should be add or update | done
68 |  | 1849 | evo(ref. 1170) amendment task | bug given
69 |  | 1931 | Bug in retail invoice Print 4 | done
70 | priority : Urgent | s-5 | speed work- changes in event 1. memo , 2. estimate , 3 . billing using advance labour policy all features specially wastage, making. | done running
71 | priority : Urgent | 1913 | mfg transaction- partially return | running
72 |  | 1894 | sale return report- add metal loss in it | done
73 | priority : Urgent | 1708 | Retail bill old gold amount | done
74 | priority : Urgent | 1829 | Discount in quotation | done
75 |  | 1955 | colorastone amount in jewellery tag 8 B | done
76 |  | 1915 | ticket move to order request | done
77 |  | 1906 | calllog-call move to ticket | done
78 |  | 1932 | Promise date in outsource report | done
79 |  | 1859 | net wt column in retail print 1 | done
80 |  | 1697 | Lab Grown in QR Tag 1 | done
81 |  | 1898 | copper optionin tag print | done
82 |  | 1664 | Whats app integration (new service provider)-2025 addon ->signup process | done
83 |  | 1979 | New Tag | done
84 |  | 1963 | merge job effect in Quality New Tag Qr | done
85 |  | 1984 | real time notification in csystem | pending
86 |  | 1981 | round off in diamond memo | bug given
87 |  | 1983 | jewellery book - dynamic implementation | done bug given
88 |  | image-sizeovercome -work | convert original into .webp | no need
89 |  | 1895 | bug in jewellery tax summary | done | done
90 |  | 1858 | filter in sprue cutting | bug given | done
91 |  | 1038 | dynamic grid | pending
92 | priority : high | 1775 | ref no in material return | done | done
93 | priority : high | 1524 | Material Sale - add discount in it | running running | done
94 |  | 1714 | Calculate ans set mrp in tag prnit | done running
95 |  | 1999 | changes in invoice print 1 | on hold | done
96 |  | 2009 | detail print S in estimate | done | done
97 |  | 1902 | Grading valuation | bug given | still bug there
98 |  | 2004 | Outsource Report-Image view with print option | done | done
99 | priority : Urgent | 1657 | closing balance in invoice print | done | done
100 | priority : Urgent | 1969 | received details from sale | done | done
101 | delivered only in elveester | 2019 | Proqc amendment - pro qc bug fixing | done
102 |  | 2014 | Add used wt checkbox- in gold demand report | bug given | still bug there
103 |  | 2011 | Purchase Report - Add Pure Wt in it | done | done
104 |  | 2013 | bug in packing list 3 (react) | bug given
105 |  | 1920 | request for add manufacture name | hold
106 | priority : Urgent | 711 | Fg stock melt in bulk | bug given | done
107 |  | 1916 | add manufacture drop down on sales job book | done | done
108 | already deliverd inclient account without testing | 1605 | Design wise stock alert | bug given | not uploaded
109 |  | 1839 | Saving Scheme - Discount for all in it | running | done
110 |  | 2037 | Lot# in Material Sale Report | done
111 |  | 1786 | design master overwrite (jewellery book) | running
112 |  | 1754 | GSTR Excel Changes Updates | running
113 |  | 1718 | Add Columns in Design Report PD | bug given | still bug there
114 |  | 1062 | centerstone | done | done
115 |  | 2044 | Center stone ctw in DX Jewellery Book | done | data not loaded
116 |  | 2021 | Credit Debit Note Reset Tax | done | done
117 |  | 2039 | power bi - Customer json | -
118 |  | 2040 | terms & condition in Packing List 7D Group | done | done
119 |  | 2041 | new tag | done | done
120 |  | 1710 | Advance Accounting | pending
121 |  | 2048 | casting analysis report -dynamic implementation | bug given
122 |  | 1755 | gstr2 excel changes | pending
123 | already deliverd in client account without testing | 1545 | sale return report -filter old tag entries | pending
124 |  | 1373 | mrp option in quotation | bug given
125 | priority : Urgent | 2029,482,2010,5090 | Artical masteri in backend attical master -shopify | running
126 | priority : Urgent | TT5090 | article Master with category size mapping | bug given
127 |  | 1350 | Stock Purchase | done
128 |  | 2012 | retail order -add apply on | running
129 |  | 1662 | Remark in Daily Statement | done
130 | priority : Urgent | 2042 | new invoice print | done
|  | R75beta | partially bug solving | 2025-11-21 11:11
131 |  | TT5188 | Amendment in Retail Invoice Print S | done
132 |  | TT5189 | amendment in Jewellery Tag TJ | done
133 |  | 1469 | option for purity in Detach material. | pending
134 | priority : high | TT5142 | Design Wise MRP | bug given
135 |  | 1995 | Add training title in training dashboard | pending
136 |  | 5179 | Feedback in training dashboard | pending
137 |  | 1889 | Invoice Excel V | done
138 |  | 2043 | live gold rate | done | done
139 |  | 1030 | From mfg design quote will create | done | bug given
140 |  | 1957 | Price Tag info- tablet camera issue | pending
141 | priority : Urgent | TT5183 | bug in detail print 5 | done
142 | priority : Urgent | 521 | Labour in Purchase Return | pending
|  | R75beta | partially bug solving | 2025-11-25 02:30
143 |  | TT5253 | changes in print Retail | done
144 |  | TT5255 | retail invoice print S in quote | done
145 |  | 1980 | estimate to advance flow | bug given
146 |  | 1813 | factory floor loss analysis dashboard | pending
147 |  | 2053 | design pd report's bug | pending
148 |  | TT5153 | detail print 5 in Quotation | done
149 |  | TT5269 | Add Amount column in Rem Diamond balance | pending
150 |  | 2046 | print for pending memo items | bug given
Upcoming Task
151 |  | 790 | Purchae Mode updatable |  |  | In Development
152 |  | 1539 | Margin Report |  |  | In Development
153 |  | 2026 | Sales Job Book - Dynamic Implementation |  |  | Work as patch
154 |  | 1642 | Customize Unified - Memo,purchase and Sale |  |  | give as patch
155 |  | 2022 | Purchase Bill Import |  |  | give as patch
156 |  | 2027 | Jewellery book - Add all amount as in rpduct cost analysis |  |  | give as patch
157 |  | 2028 | Tag split - multi metal not working |  |  | In Development
158 |  | 2034 | Remarks update in Quotation |  |  | give as patch
159 |  |  | Brokerage in stock purchase
160 |  |  | Job wise flag for order wise policy
161 | need in R74 priority : Urgent | 1438 | Stock Valuation | in development
162 |  | 1543 | sales QC Master | in development
163 |  | 1538 | discount limit employee wise | on hold
Note on C73: bug
Note on C137: Refer new iTask (optigohub) for document